HIRECAR

WORKSPACE 4

Execution Monitor & Deadline Enforcer

Track all workspaces, enforce deadline, identify blockers, produce status reports

| Timeline | 4:00 PM → 11:59 PM PST (continuous) |
| --- | --- |
| Date | March 3, 2026 |
| Deadline | 11:59 PM PST |

Engineering consent, not just delivering services.

# Mission Statement

This workspace does NOT build anything. It tracks all three workspaces, enforces the 11:59 PM PST deadline, identifies blockers in real-time, reallocates tasks if a workspace falls behind, and produces status reports every 90 minutes. Workspace 4 is the air traffic controller of tonight's execution.

NOTE: Workspace 4 starts IMMEDIATELY and runs until the final deadline. It has no dependencies — it monitors the other three workspaces. The Execution Monitor must be ruthlessly honest about progress.

# Escalation Protocol

| Rule | Condition | Action |
| --- | --- | --- |
| Rule 1 | Any workspace > 30 min behind at checkpoint | Reassign lowest-priority tasks to furthest-ahead workspace |
| Rule 2 | 8:30 PM critical checkpoint fails ANY of 4 conditions | ALL workspaces stop P2, focus exclusively on failed conditions |
| Rule 3 | 11:00 PM Code Freeze | No new tasks started. All effort on completing in-progress + integration test. |

# Critical Checkpoint Criteria (8:30 PM)

ALL FOUR conditions must be TRUE to proceed normally. If ANY is FALSE, trigger Rule 2 emergency focus.

| # | Condition | Source | Status |
| --- | --- | --- | --- |
| 1 | Payment pipeline works end-to-end (Stripe test passes) | WS1 Task 1.11 | [ ] PASS / FAIL |
| 2 | Enrollment bot processes test member successfully | WS2 Task 2.11 | [ ] PASS / FAIL |
| 3 | At least 2 playbook chapters live on BitDocs | WS3 Tasks 3.1-3.2 | [ ] PASS / FAIL |
| 4 | Enrollment form posts data to Make.com webhook | WS3 Task 3.9 | [ ] PASS / FAIL |

# Task Execution

## Task 4.1: Initial Status Check — All Workspaces (4:00 PM)

| Priority: P0 | Time: 15 min | Task ID: 4.1 | Output: Status report #1 |
| --- | --- | --- | --- |

### Instructions

- Verify owner pre-actions have STARTED: Check if Stripe account creation is in progress. Check if Zoho Mail setup is in progress. Check if GoDaddy DNS changes are in progress.

- Verify WS1 has begun: Confirm the WS1 executor is online and working on task 1.1 or 1.10 (whichever can start first).

- Verify WS3 has begun: Confirm the WS3 executor is online and has started on playbook Chapter 1 (task 3.1) or dispute templates (task 3.5).

- Verify WS2 is scheduled: Confirm the WS2 executor understands they start at 5:00 PM and has reviewed their task list.

- Document blockers: List any owner pre-actions not yet started. Flag P0 blockers.

- Compile Status Report #1 and distribute to all workspace executors.

- Format: WS1: [status] | WS2: [status] | WS3: [status] | Blockers: [list] | Owner Actions: [list]

### Directions

- Communication channel: Use Slack #hirecar-ops (if set up) or text/email to the team.

- This is the first checkpoint. Set the tone: be factual, be specific, be constructive.

- If owner pre-actions have not started, this is the #1 escalation. Nothing else can proceed.

- Status report template (fill in for each checkpoint, adapt as needed):

## Task 4.2: Status Check — 5:30 PM PST

| Priority: P0 | Time: 15 min | Task ID: 4.2 | Output: Status report #2 |
| --- | --- | --- | --- |

### Instructions

- Check WS1 progress: Tasks 1.1-1.4 should be complete or nearly complete. If not, identify why.

- Check WS2 startup: Has WS2 started? Are Make.com data stores ready (WS1 task 1.10)?

- Check WS3 progress: Is playbook Chapter 1 in progress? Are dispute templates started?

- Check owner DNS: Is DNS propagating? Use whatsmydns.net to check MX records for hirecar.la.

- Identify cross-workspace blockers: Is anything in WS1 blocking WS2? Is anything in WS3 blocking WS1?

- Apply Rule 1 if needed: If any workspace is > 30 min behind, reallocate their lowest-priority task.

- Compile Status Report #2.

### Directions

- 5:30 PM is 1.5 hours in. WS1 should have the foundational P0 tasks done.

- DNS propagation: MX records typically take 1-4 hours. If not propagated yet, this is normal.

- WS2 dependency: If data stores (WS1 1.10) are not ready, WS2 should work on tasks 2.4 and 2.6 (logic modules that do not require data stores).

- Keep reports concise. Workspace executors are busy building.

## Task 4.3: Status Check — 7:00 PM PST

| Priority: P0 | Time: 15 min | Task ID: 4.3 | Output: Status report #3 |
| --- | --- | --- | --- |

### Instructions

- Check WS1: Payment Pipeline scenario (1.2) should be built and in testing. If not, this is concerning.

- Check WS2: Enrollment Bot workflow (2.1) should be designed, build (2.2) in progress.

- Check WS3: Dispute templates (3.5) should be done or nearly done. At least 1 playbook chapter complete.

- Check integration points: Can WS2 connect to WS1 data stores? Has WS3 delivered the enrollment form HTML to WS1/WS2?

- Flag if enrollment form (3.9) is not delivered: This blocks WS1 task 1.3 (lead capture test) and WS2 task 2.11 (E2E test).

- Calculate completion percentage for each workspace.

- Compile Status Report #3. Include time-to-deadline estimate.

### Directions

- 7:00 PM = 3 hours in, 5 hours to deadline. This is the midpoint.

- If any P0 task is not started by now, escalate immediately.

- Enrollment form is a critical dependency. If WS3 has not delivered it, they should prioritize it NOW over playbook chapters.

- Completion %: Count tasks done / total tasks. Weight P0 tasks 3x.

## Task 4.4: CRITICAL CHECKPOINT — 8:30 PM PST

| Priority: P0 | Time: 20 min | Task ID: 4.4 | Output: Go/No-Go decision |
| --- | --- | --- | --- |

### Instructions

- This is the GO / NO-GO decision point. Evaluate all 4 conditions from the Critical Checkpoint Criteria table above.

- Condition 1 — Payment Pipeline: Ask WS1 to run the Stripe test NOW if not already done. Result must be: webhook fires, Make.com processes, email sends, Slack notifies.

- Condition 2 — Enrollment Bot: Ask WS2 to run the enrollment test NOW. Result must be: form data received, member record created, welcome email sent.

- Condition 3 — Playbook Chapters: Check BitDocs. Are at least 2 chapters published? Open them and verify they have real content.

- Condition 4 — Enrollment Form: Load the form in a browser. Fill it in and submit. Does data arrive in Make.com?

- If ALL 4 PASS: Continue with P1 and P2 tasks. Target maximum completion by 11:59 PM.

- If ANY FAIL: Execute Rule 2 — ALL workspaces stop P2 tasks. Focus EXCLUSIVELY on the failed condition(s).

- Document the Go/No-Go decision with specific pass/fail for each condition.

- Compile Status Report #4 (Critical Checkpoint Report).

### Directions

- This is the most important checkpoint of the night. Be thorough and honest.

- Do NOT mark a condition as PASS if it partially works. It must work end-to-end.

- If Rule 2 is triggered, communicate immediately to all workspaces. Be specific about what needs to happen.

- If 2 or more conditions fail, consider whether 50% operational is achievable by deadline.

## Task 4.5: Status Check — 9:30 PM PST

| Priority: P0 | Time: 15 min | Task ID: 4.5 | Output: Status report #5 |
| --- | --- | --- | --- |

### Instructions

- Check WS1: Hosting deployed (Cloudflare + Vercel)? If not, is it critical for tonight?

- Check WS2: All P0/P1 bots done? Are integration tests passing?

- Check WS3: Homepage and landing pages ready? T&C written?

- Check remaining work: List all incomplete tasks across all workspaces.

- Prioritize remaining work: What can realistically be finished in 2.5 hours?

- Apply triage: Move anything that will not be finished to the Tomorrow list.

- Compile Status Report #5.

### Directions

- 9:30 PM = 1.5 hours before Code Freeze. Reality check time.

- Hosting (Cloudflare/Vercel) is P2. If the core payment + enrollment + playbook flow works, hosting can wait.

- Focus: What is the minimum viable product we can deliver by 11:59 PM?

- Start building the final completion report mentally.

## Task 4.6: INTEGRATION TEST — 10:30 PM PST

| Priority: P0 | Time: 30 min | Task ID: 4.6 | Output: Integration test report |
| --- | --- | --- | --- |

### Instructions

- This is the FULL SYSTEM TEST. Every component must work together.

- Test Step 1: Open the HIRECAR homepage (or enrollment form URL). Verify it loads.

- Test Step 2: Click the enrollment CTA. Verify the enrollment form loads.

- Test Step 3: Fill in the form with test data. Submit. Verify the webhook fires in Make.com.

- Test Step 4: Check Make.com execution: Lead Capture scenario ran, enrollment route activated, member record created in Members data store.

- Test Step 5: Check email: Welcome email received by the test email address.

- Test Step 6: Check Slack: New member notification appeared in #hirecar-ops.

- Test Step 7: Process a Stripe test payment for the new test member. Verify: Payment Pipeline fires, confirmation email sent, Slack notification posted, member status updated.

- Test Step 8: Check BitDocs: Navigate to playbook Chapter 1. Verify content is accessible.

- Document results for EACH step: PASS / FAIL with details on any failures.

- Compile Integration Test Report.

### Directions

- This test simulates a real member journey from first contact to payment.

- If any step fails, immediately assign the fix to the appropriate workspace executor.

- Priority of fixes: revenue flow > enrollment flow > content > notifications.

- Use a test email address you can actually check (not example.com).

- If the homepage is not ready, start at Step 2 (direct to enrollment form URL).

## Task 4.7: Final Fixes — 10:30 PM to 11:30 PM

| Priority: P0 | Time: 60 min | Task ID: 4.7 | Output: Fixes applied |
| --- | --- | --- | --- |

### Instructions

- Address failures from the integration test in priority order.

- Priority 1: Revenue flow (payment pipeline). If Stripe webhook is not connecting, debug the webhook endpoint.

- Priority 2: Enrollment flow (form > Make.com > member record > email). If form does not submit, check the webhook URL.

- Priority 3: Content availability (playbook chapters on BitDocs). If chapters are not published, publish now.

- Priority 4: Notifications (Slack + email). If not sending, check connections in Make.com.

- For each fix: Apply the fix > Re-test that specific step > Confirm PASS.

- At 11:00 PM: CODE FREEZE (Rule 3). No new tasks. Only finish in-progress fixes.

- At 11:15 PM: Run a final quick integration test on any steps that were fixed.

- At 11:30 PM: Stop all work. Begin compiling the final report.

### Directions

- This is crunch time. Be decisive and focused.

- If a fix requires more than 30 minutes, it should be deferred to tomorrow. Focus on what can be fixed quickly.

- Code Freeze at 11:00 PM is FIRM. Starting new tasks this late risks introducing new bugs.

- Quick test after fixes: Just run through the failing steps, not the full integration test.

## Task 4.8: FINAL STATUS REPORT — 11:45 PM PST

| Priority: P0 | Time: 15 min | Task ID: 4.8 | Output: Final report |
| --- | --- | --- | --- |

### Instructions

- Compile the comprehensive final report for the owner.

- Section 1 — What Shipped Tonight: List every capability that is working end-to-end. Include the integration test results.

- Section 2 — What Is 50%+ Complete: List tasks that are partially done and can be finished quickly tomorrow.

- Section 3 — What Is Deferred: List all tasks moved to Phase 2 with reason.

- Section 4 — Critical Issues: Any unresolved bugs or failures that need attention first thing tomorrow.

- Section 5 — Success Criteria Check: Go through the 12-item Success Criteria table from the Execution Plan. Mark YES/NO for each.

- Section 6 — Recommended Next Steps: Top 5 priorities for tomorrow morning.

- Send the final report to the owner and post to #hirecar-ops Slack.

- Archive all status reports and test results.

### Directions

- Be honest. Do not inflate results. The owner needs accurate information to plan tomorrow.

- Success criteria: Accept Payments, Capture Leads, Enroll Members, Generate Invoices = MUST HAVE. Everything else is bonus.

- Format the report clearly. Use pass/fail checkmarks. Include timestamps.

- This report is the permanent record of tonight's execution sprint.

# Questions for the Owner

Operational decisions for the Execution Monitor.

## Communication & Authority

- What communication channel should status reports be sent to? Slack #hirecar-ops? Email? Text? All three?

- Does the Execution Monitor have authority to reallocate tasks between workspaces, or does this require your approval?

- If a workspace executor is unresponsive for > 30 minutes, what is the escalation path?

- Who is the emergency contact if YOU (the owner) are unreachable during a critical blocker?

## Decision Authority

- If the 8:30 PM critical checkpoint fails, should we: (a) Continue pushing for 50% by midnight, or (b) Stop, reassess, and plan a new timeline?

- What is the absolute minimum you need shipped tonight to consider the sprint a success? (Rank: payments, enrollment, playbook, website)

- If Make.com Free plan limits are hit mid-execution, do you authorize an immediate upgrade to Core ($9/mo)?

- Should we publish the site to hirecar.la tonight (replacing Wix) or deploy to a staging subdomain first?